## Week 5
Task | Assigned to | Estimated effort (in hours) | Actual effort (in hours) | Done | Notes
Create scheduled request object | Bink Boëtius | 0.5 | 1.5 | TRUE | Still some more tests needed before it's safe to merge.
Create feature to get requests from schedule from a specific date | Bink Boëtius | 1.5 | 2.5 | TRUE | Still some more tests needed before it's safe to merge.
Create feature to add request to schedule on specific date | Bink Boëtius | 1 | 1.5 | TRUE | Still some more tests needed before it's safe to merge.
Refactor schedule microservice to make use of commons module | Bink Boëtius | 1 | 3.5 | TRUE | Took way longer than expected due to problems with GitKraken and Intellij
Create database for User microservice and service to use it | Ivans Kravcevs | 5 | 5 | TRUE
Create external APIs for users in User microservice | Ivans Kravcevs | 5 | 5 |  | Part of it is done, APIs for faculty admins and sysadmins should be added
Create internal APIs for User microservice communication with WaitingList and Authentication | Ivans Kravcevs | 3 | 5 | TRUE | Communication with other microservices will be added during the next week
Add accepting requests in waitinglist | Michiel Bakker | 5 | 6 | FALSE | Already made a big part.
Add showing request by faculty | Michiel Bakker | 4 | 3 | FALSE | All most finished, only still have to solve checkstyle issue
Create common module | Nils | 0.5 | 1.5 | TRUE
Create waiting list with functionality to add new requests | Nils | 3 | 9 | TRUE
Add role functionality to authentication microservice | Radu Ionut Ciobanu | 4 | 8 | TRUE
Implement role checking functionality in every other microservice | Radu Ionut Ciobanu | 15 | 3

## Week 6
Task | Assigned to | Estimated effort (in hours) | Actual effort (in hours) | Done | Notes
Implement role functionality in every microservice | Radu Ionut Ciobanu | 10 | 10 | TRUE | Had to refactor a lot of old code after realising spring had a better way of doing this
Implement resource microservice | Radu Ionut Ciobanu | 18 | 18 | TRUE | Node dropping functionality has been ignored after discussing with the TA
Implement node adding functionality | Radu Ionut Ciobanu | 4 | 4 | TRUE | Subtask of Resource Microservice
Implement resource releasing functionality | Radu Ionut Ciobanu | 5 | 5 | TRUE | Subtask of Resource Microservice
Implement used resource tracking | Radu Ionut Ciobanu | 6 | 6 | TRUE | Subtask of Resource Microservice
Creating Adapter design pattern | Ivans Kravcevs | 5 | 5 | TRUE
Finishing and testing all APIs in User microservice | Ivans Kravcevs | 10 | 20 | TRUE
Creating Strategy design pattern | Ivans Kravcevs | 5 | 5 | TRUE
Add functionality for rejecting requests to waiting list | Nils | 3 | 1.5 | TRUE
Automatically reject pending requests 5 minutes before deadline | Nils | 5 | 4 | TRUE
Postman tests | Nils | 8 | 8 | TRUE | This was not fun, but at least I found some bugs.
Implement approve request functionality | Michiel Bakker | 6 | 12 | TRUE | Need to reimplement a big part because I did it wrong, also needed to wait for scheduler microserves and implement authentication.
Implement automatic approval 6 hours before deadline | Michiel Bakker | 7 | 14 | TRUE | Because of merge multiple times into this branch it got corrupted, it to me a long time to make it work again.
Write tests for User API | Michiel Bakker | 2 | 2 | TRUE | Not all tests I wanted, because it would take to long to get everything in GitLab
Writing tests for Schedule microservice basic functionality (last sprint) | Bink Boëtius | 3 | 14 | TRUE | Due to a lot of errors in dependencies, other bugs in the IDE and merge conflicts, it took a lot of time to get the tests done and the branch merged.
Add checking and updating available resources when scheduling request | Bink Boëtius | 1.5 | 3.5 | TRUE | Took longer due to merge conflicts with other branches.
Fix role authorization at schedule microservice | Bink Boëtius | 1 | 1 | TRUE
Update README file | Bink Boëtius | 3 | 5 | TRUE | There were more endpoints to explain then expected.